## Summary
PRISM CIH Web - Validation & Restriction Audit
Audit date 2026-10-03 ¦ branch dev ¦ static review of src/app and lambda-functions/. Counts are live formulas over the detail sheets.
Area | Done | Partial | Missing | Total | % Done
Client-side rules
Server-side: auth check per Lambda
System restrictions
Total
Other counts
P1 critical gaps
P1 gaps still open
Endpoints with no source in repo
Lambda rows reviewed
How to use
- Track fixes in 'Fix Status' (P1 Critical) and 'Status' (Fix Order): Open / In progress / Fixed.
- When a rule is fixed, set its Status on the detail sheet to Done; the table above recalculates.
- Status values: Done, Partial, Missing, Unknown (= source not in repo).

## P1 Critical
Top Priority Gaps (P1)
Source: docs/VALIDATION_AUDIT.md ¦ audit date 2026-10-03 ¦ branch dev ¦ static code review
# | Priority | Gap | Where | Impact | Fix Status
1 | P1 | No caller / role check on the generic update endpoint | prismMultiplefieldupdate.js | Any user can update ROLE_PAGE_ACCESS (grant own role any page), MEM_MEMBERS (no-longer-patient flag), plans, attachments, tasks | Open
2 | P1 | No caller / role check on the bulk update endpoint | prismMultipleRowAndFieldUpdate.js | Any user can set MEM_OUTREACH_MEMBERS.Care_Coordinator_id to themselves, which bypasses every ownership check in the select/gap Lambdas | Open
3 | P1 | No caller check on prismMultipleRowInsert.js (it also lists ROLE_PAGE_ACCESS) | prismMultipleRowInsert.js | Anonymous inserts; non-admin can insert page-access rows (the admin gate exists only in prismMultipleinsert.js) | Open
4 | P1 | Password reset of any account with no auth | prismUpdateCognitoUser.js (TODO in code) | Account takeover: anyone can set any user's Cognito password | Open
5 | P1 | DB password update with no ownership check | prismUserPasswordUpdate.js (TODO in code) | Any user can change any user's DB password by ID | Open
6 | P1 | User creation with no admin check | prismCreateCognitoUser.js, prismCreateUser.js (TODO in code) | Anyone can create login-capable accounts with any role_id (including Admin = 7) | Open
7 | P1 | Attachment delete with no auth/ownership | prismdeleteAttachment.js (TODO in code) | Delete any attachment + S3 object by enumerating ids | Open
8 | P1 | Lockout reset is unauthenticated | loginSuccessReset.js | Anyone can clear the failed-attempt counter for any user, so lockout is ineffective | Open
9 | P1 | Stored XSS | calllist-dialog.service.ts builds HTML with unescaped action_note, action_type, action_result, then bypassSecurityTrustHtml | A note typed in Add Action runs script for anyone viewing call history | Open
10 | P1 | Cognito client secret shipped in the browser bundle | environments/environment.ts -> auth.service.ts calculateSecretHash | Secret is public; app client should be a public client (no secret) | Open
11 | P1 | No route guards; role/page access is client-only | app.routes.ts (0 canActivate), header.service.ts | Page access is checked after the component loads, from localStorage (user-editable). The real protection is only the per-Lambda checks, and items 1–7 lack them | Open
12 | P1 | Expired password not enforced | login.ts stores user + Cognito tokens before the expiry check; prismAuthentication.js still returns 200 | User with an expired password can browse straight to /dashboard | Open
13 | P1 | prismUpdatePlanyearForRiskgap.js has no auth or member ownership check | Lambda | Any caller can change PLAN_YEAR on any member's risk gaps | Open
14 | P1 | Audit fields trusted from client | All inserts (added_by, add_by, log_by, refer_by, ADDED_BY) | MEM_SYSTEM_LOG and ownership columns can be spoofed; should be set from caller sub server-side | Open

## Client-Side
Client-Side Validation - Page by Page
Source: docs/VALIDATION_AUDIT.md ¦ audit date 2026-10-03 ¦ branch dev ¦ static code review
Page / Dialog | Field / Rule | Status | Notes / What is missing
Login (/login) | Username, password required | Done | HTML required
Login (/login) | OTP 6 digits | Done | maxlength=6, pattern=[0-9]*, auto-submit at 6
Login (/login) | MFA (TOTP setup + verify) | Done | Via Cognito
Login (/login) | Failed-attempt counter + lock message | Partial | Driven by the client (loginFailedIncrement -> prismLockedCognitoUser). Skipped if the API is called directly. prismLockedCognitoUser now requires Admin, so a non-logged-in user's call will get 401/403. Verify that lockout still disables the Cognito user.
Login (/login) | Username email-format / trim | Missing | Add Validators.email + trim
Login (/login) | Expired password blocks login | Missing | See P1 #12. Do not call setUser (or keep tokens) until the expiry check passes
Change Password (/change-password) | New = Confirm | Done
Change Password (/change-password) | >=15 chars, upper, lower, digit, special | Done | In validatePasswordPolicy
Change Password (/change-password) | HTML minlength="8" | Partial | Conflicts with the 15-char policy; change it to 15
Change Password (/change-password) | Special-char set | Partial | Client allows only !@#$%^&*; server accepts any non-alphanumeric character. Align them
Change Password (/change-password) | Current password required | Missing
Change Password (/change-password) | New != old / password history | Missing
Change Password (/change-password) | Password must not contain name/email | Missing
Manage Users – Add/Edit User dialog | First / Last name required | Done | Trimmed on submit
Manage Users – Add/Edit User dialog | Role, Department, Status required | Done
Manage Users – Add/Edit User dialog | Email required + format | Partial | Validators.email accepts a@b; server requires a dot. Use the same regex
Manage Users – Add/Edit User dialog | Email duplicate check | Done | checkuserexist (server also returns 409 on unique violation)
Manage Users – Add/Edit User dialog | Password | Partial | Only minLength(6), but the hint and server require 15 + complexity. Add the same policy validator
Manage Users – Add/Edit User dialog | Confirm password | Missing
Manage Users – Add/Edit User dialog | Name max length (100) / email (150) | Missing | Server enforces it; client should too
Manage Users – Add/Edit User dialog | Name pattern (letters, space, -, ') | Missing
Manage Users – Add/Edit User dialog | Whitespace-only names | Partial | Pass required; rejected by server after trim
Manage Users – Add/Edit User dialog | Admin cannot deactivate self or remove own Admin role | Missing
New User Account Request dialog | First, last, email, phone, role, date, status required | Done
New User Account Request dialog | Email format | Done | Same a@b weakness
New User Account Request dialog | Phone auto-format (xxx) xxx-xxxx, maxlength 14 | Done
New User Account Request dialog | Phone exactly 10 digits | Missing | (12 passes required
New User Account Request dialog | Duplicate email (existing user / pending request) | Missing
New User Account Request dialog | Request date not in future | Missing
New User Account Request dialog | Status should not be selectable on create | Missing
New User Account Request dialog | Names length / pattern / trim | Missing
New User Account Request dialog | Error shown to user | Missing | handleError only logs to the console
Alternate Address dialog | Address, city, state, zip required | Done
Alternate Address dialog | Zip auto-format, maxlength 10 | Done
Alternate Address dialog | Zip exactly 5 or 9 digits | Missing | 123 passes
Alternate Address dialog | State = valid 2-letter code (dropdown) | Missing | Free text
Alternate Address dialog | Length limits, trim, whitespace-only | Missing
Alternate Address dialog | Duplicate address check | Missing
Alternate Address dialog | Failure message to user | Missing | Console only
Alternate Phone dialog | Required, auto-format, maxlength 14 | Done
Alternate Phone dialog | Exactly 10 digits | Missing
Alternate Phone dialog | Not duplicate of primary/other alt phone | Missing
Alternate Phone dialog | Failure message to user | Missing
Manage Plans – Plan dialog | Name, start, end, status required | Done
Manage Plans – Plan dialog | Start <= End | Done | Via alert(), not a form validator
Manage Plans – Plan dialog | Duplicate plan name | Missing
Manage Plans – Plan dialog | Name length / trim | Missing
Assign Plan dialog | Plan required | Done
Assign Plan dialog | Already-assigned check | Done | checkplanexist per member (stops at first hit, but doesn't say which member)
Assign Plan dialog | Only active / in-date plans selectable | Missing
File Attachment dialog (Plans / User requests) | File required (new), status required | Done
File Attachment dialog (Plans / User requests) | File type allow-list (accept + extension check) | Missing | Any file can be uploaded
File Attachment dialog (Plans / User requests) | Max file size / empty file | Missing
File Attachment dialog (Plans / User requests) | Delete confirm | Partial | Native confirm()
Task dialog | Activity, date, assign-to, status required | Done
Task dialog | Task date not in past (new task) | Missing
Task dialog | Note max length | Missing
Transfer Member dialog | Department, user required | Done
Transfer Member dialog | Cannot transfer to current owner | Missing
Transfer Member dialog | Reason required / length | Missing | Optional today
No-Longer-Patient confirm / Unlock-User confirm | Note required, trimmed | Done
No-Longer-Patient confirm / Unlock-User confirm | Whitespace-only blocked on client | Partial | Passes required; server rejects blank (no-longer-patient only)
No-Longer-Patient confirm / Unlock-User confirm | Note max length | Missing
Rolewise Page Access dialog | Role, page, status required | Done
Rolewise Page Access dialog | Duplicate role + page combination | Missing
Rolewise Page Access dialog | Prevent Admin removing own access to this page | Missing
Add Action (member action panel) | Action date valid; keys limited to digits and /; maxlength 10 | Done
Add Action (member action panel) | Quality gap: TIN, Provider, DOS, RxProviderFlag, PCPFlag, SuppSource required | Done
Add Action (member action panel) | Quality gap: at least one of CPT / HCPCS / ICD-10 | Done
Add Action (member action panel) | TIN/Provider conditional required | Done
Add Action (member action panel) | LOINC answer reset when LOINC cleared | Done
Add Action (member action panel) | Appointment: vendor, provider, date, time, status, place, type required | Done
Add Action (member action panel) | PCP visit: date + type required, valid date | Done
Add Action (member action panel) | Star measure: measure, date, count, TIN required + duplicate check | Done
Add Action (member action panel) | Next activity date required when Next activity chosen | Missing | Otherwise action_date is null and the server returns 400
Add Action (member action panel) | Action date / DOS / PCP visit date not in future | Missing
Add Action (member action panel) | Next action date >= today | Missing
Add Action (member action panel) | Appointment date not in past | Missing
Add Action (member action panel) | NPI = 10 digits (+ Luhn check) | Missing
Add Action (member action panel) | Taxonomy code format (10 chars) | Missing
Add Action (member action panel) | ICD-10 / CPT / HCPCS format | Missing
Add Action (member action panel) | Risk-gap rows: any required fields | Missing | Only quality gaps are validated
Add Action (member action panel) | Note fields max length | Missing
Process File pages (Member / Risk / Quality / PCR / Star Performance) | File required, .csv extension | Done | All 5
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Exact header match | Done | Member, Risk, Quality, PCR ¦ ❌ Star Performance (dynamic date columns)
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Empty file (< 2 rows) | Done | Member
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Date normalisation | Done
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Max file size / row count | Missing
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Row-level checks (required columns, Medicaid ID format, numeric, valid dates) | Missing
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Bad rows reported | Missing | Member file silently skips rows whose column count differs
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Quoted CSV values | Partial | Member file uses split(','), so values containing commas break. Others use Papa Parse
Process File pages (Member / Risk / Quality / PCR / Star Performance) | Duplicate rows within the file | Missing
Reports | Appointments, Action Log, Outreach, Gaps, System Log | Done | Start/end required + end >= start (group validator)
Reports | File Log Report | Done | Type + list required
Reports | Max date range | Missing | Only the server enforces it, and only in prismLogdetailsbymedicaid
Reports | Future dates | Missing
Reports | Member Risk, Star Performance | Missing | No validation (year/plan)
Reports | CSV export formula escaping (=, +, -, @) | Missing | CSV injection risk
Global client restrictions | Inactivity logout (10 min) | Done | auth.service.ts
Global client restrictions | Token refresh + retry on 401 | Done | token.interceptor.ts
Global client restrictions | Sidebar hides menus by role | Done | Cosmetic only
Global client restrictions | Page access check (HeaderService.setTitle) | Partial | Runs after the component loads; reads localStorage
Global client restrictions | Route guards (auth + role) | Missing
Global client restrictions | Global 403 handler | Missing
Global client restrictions | Integer-only directives exist | Partial | appIntegerOnly / appIntegerPositiveOnly are never used in any template
Global client restrictions | Storage encryption | Missing | storageEncryption: false; key derived from a function name; CryptoService hard-coded key
Global client restrictions | console.log in source | Partial | 18 occurrences; remove any PHI from them

## Server-Side
Server-Side Validation - Lambda by Lambda
Source: docs/VALIDATION_AUDIT.md ¦ audit date 2026-10-03 ¦ branch dev ¦ static code review
Lambda | Auth (caller sub) | Role / Ownership | Input validation done | Missing
prismAuthentication | n/a (login) | – | username/password required; bcrypt; lock check (423); active users only | Doesn't increment failed attempts itself; returns 200 when password expired; returns all roles' page access
loginSuccessReset | Missing | Missing | username required | P1 #8
prismLockedCognitoUser | Done | Done - Admin | username required | Conflicts with the login lockout flow (see 1.1)
prismAdminUnLockedCognitoUser | Done | Done - Admin | username required | –
prismUserPasswordUpdate | Missing | Missing | ID, password required; 15-char policy | P1 #5; ID integer check
prismUpdateCognitoUser | Missing | Missing | username required; attribute allow-list; policy | P1 #4; returns 500 for missing username (should be 400)
prismCreateCognitoUser | Missing | Missing | email format; policy; numeric role | P1 #6
prismCreateUser | Missing | Missing | required; trim; length; email; ints; status ∈ {0,1}; policy; 409 on duplicate | P1 #6; role/department exist in master tables
prismUpdateUser | Done | Done - Admin | required; ints; status; optional policy | Name length/trim; role/department exist; Admin can't demote self
prismMultipleinsert | Done | Partial - Admin only for ROLE_PAGE_ACCESS | table allow-list; required fields per table; identifier check; batching | Column allow-list per table; member ownership for medicaid_id rows; audit fields from caller; type/format/length checks (phone, zip, email, dates); max rows; MEM_GAP_OBSERVATION_DATA and *_TEMP have no required fields; temp tables not Admin-gated
prismMultipleRowInsert | Missing | Missing | table allow-list; required fields | P1 #3 (same gaps as above)
prismMultiplefieldupdate | Missing | Missing | table + id-column allow-list; required fields; no blank values | P1 #1; column allow-list (any column of an allowed table can be set)
prismMultipleRowAndFieldUpdate | Missing | Missing | table + id-column allow-list; identifier check | P1 #2; column allow-list; max rows; values not checked
prismUploadplandocument | Done | Done - Admin, or page access + owner | filename safe; directory allow-list; id integer; env pattern; bucket fixed | fileType / extension allow-list; size limit (use presigned POST with content-length-range); prod code allows http:// dev + localhost origins
prismdeleteAttachment | Missing | Missing | id integer | P1 #7
prismdeleteGapObservations | Done | Partial - owner by subscriber | <=500 records; id integer; subscriber required; Type ∈ risk/quality | Record id is not verified to belong to its subscriber_number (pair an owned subscriber with any id); Admin gets 403 (no Admin bypass)
prismUpdategapStatus / prismUpdatequalityStatus | Done | Done - Admin or owner | medicaid_id required; diag codes non-empty | action_id integer check; code format
prismUnSetMemberGapsStatus / prismUnSetqualityStatus | Done | Done - Admin or owner | medicaid_id required | action_id type (bound as VarChar in one)
prismUpdatePlanyearForRiskgap | Missing | Missing | required; year range 2000...current+1 | P1 #13
prismProcess{Members,PCR,QualityGaps,RiskGaps}... | Done | Done - Admin | session_id numeric | Validation of staged rows before commit
prismProcessStarPerformanceSeccionID | Unknown | Unknown | ? | Source not in repo (stub only)
prismGetUserMemberList | Done | Done - non-admin forced to self | – | –
prismGetMemberGapsList, prismGetcallhistory, prismMemberAllDetails | Done | Done - Admin or owner | medicaid_id required | year params unchecked (gaps)
prismGetappointmentList | Done | Done - Admin or owner | dates parsed | Max range
prismGetMemberUpcommingTaskList | Done | Done - non-admin forced to self | – | –
prismLogdetailsbymedicaid | Done | Done - Admin | dates required, valid, end >= start, max range | –
prismGetPageAccessList, prismUserslist | Done | Done - Admin | – | –
prismGetproviderIdByTin | Missing | Missing | TIN = 9 digits | Auth (low risk, reference data)

## Missing Endpoints
Endpoints Called by UI With No Source in Repo
Source: docs/VALIDATION_AUDIT.md ¦ audit date 2026-10-03 ¦ branch dev ¦ static code review
# | Endpoint | Status | Action
1 | loginFailedIncrement | Not in repo | Add source to repo; apply auth + ownership checks
2 | loginOtpInput | Not in repo | Add source to repo; apply auth + ownership checks
3 | pismGetbenefits | Not in repo | Add source to repo; apply auth + ownership checks
4 | prismActionresultfollowup | Not in repo | Add source to repo; apply auth + ownership checks
5 | prismFileProcessLoglistBySession | Not in repo | Add source to repo; apply auth + ownership checks
6 | prismFileProcesslistByType | Not in repo | Add source to repo; apply auth + ownership checks
7 | prismGetAddActionMasterData | Not in repo | Add source to repo; apply auth + ownership checks
8 | prismGetMemberPCPVisitList | Not in repo | Add source to repo; apply auth + ownership checks
9 | prismGetProviderListByVendorId | Not in repo | Add source to repo; apply auth + ownership checks
10 | prismGetStarPerformanceByYear | Not in repo | Add source to repo; apply auth + ownership checks
11 | prismGetTempMembersBySeccionID | Not in repo | Add source to repo; apply auth + ownership checks
12 | prismGetTempQualityGapsBySeccionID | Not in repo | Add source to repo; apply auth + ownership checks
13 | prismGetTempRiskGapsBySeccionID | Not in repo | Add source to repo; apply auth + ownership checks
14 | prismGetTempStarPerformanceBySeccionID | Not in repo | Add source to repo; apply auth + ownership checks
15 | prismGetUserByEmail | Not in repo | Add source to repo; apply auth + ownership checks (email-enumeration risk if open)
16 | prismGetattachmentListbytypeId | Not in repo | Add source to repo; apply auth + ownership checks
17 | prismGetcihpcr | Not in repo | Add source to repo; apply auth + ownership checks
18 | prismGetgapList | Not in repo | Add source to repo; apply auth + ownership checks
19 | prismGetgapsobservationdata | Not in repo | Add source to repo; apply auth + ownership checks
20 | prismGetqualityList | Not in repo | Add source to repo; apply auth + ownership checks
21 | prismGetuserlistbyrole | Not in repo | Add source to repo; apply auth + ownership checks
22 | prismGetusersbydeptid | Not in repo | Add source to repo; apply auth + ownership checks
23 | prismLogbyuserid | Not in repo | Add source to repo; apply auth + ownership checks
24 | prismMemberriskprofile | Not in repo | Add source to repo; apply auth + ownership checks
25 | prismOutreachmemberSP | Not in repo | Add source to repo; apply auth + ownership checks
26 | prismPlanexist | Not in repo | Add source to repo; apply auth + ownership checks
27 | prismUserRequestList | Not in repo | Add source to repo; apply auth + ownership checks
28 | prismUsers | Not in repo | Add source to repo; apply auth + ownership checks
29 | prismVendorListByplan | Not in repo | Add source to repo; apply auth + ownership checks
30 | prismVendorMasterlist | Not in repo | Add source to repo; apply auth + ownership checks

## System Restrictions
System-Wide Restriction Checklist
Source: docs/VALIDATION_AUDIT.md ¦ audit date 2026-10-03 ¦ branch dev ¦ static code review
Area | Restriction | Status | Notes
Authentication | Cognito login + TOTP MFA | Done
Authentication | Cognito authorizer on API Gateway for all routes | Partial | Confirmed on some; login-flow routes have none
Authentication | Client secret not in browser | Missing
Session | 10-min inactivity logout | Done
Session | Token refresh | Done
Session | Tokens in localStorage (XSS-exposed) | Partial
Password | 15+ chars & complexity on server (create / update / reset) | Done
Password | Same policy on client (Add User) | Missing | (6 chars)
Password | Expiry warning + expiry | Partial | Shown, not enforced
Password | History / no-reuse | Missing
Lockout | Lock after N failures | Partial | Client-driven; reset endpoint is open
Lockout | Admin unlock with note | Done
Authorization | Role-based menu | Done | (UI only)
Authorization | Route guards | Missing
Authorization | Server role checks | Partial | Done on ~60% of the Lambdas in the repo; missing on the generic update/insert and user/password endpoints
Authorization | Member ownership (navigator sees only own members) | Partial | Done on reads; bypassable through P1 #2; missing on member-level inserts
Data input | SQL parameterisation | Done | Everywhere reviewed
Data input | Table / id-column allow-lists | Done
Data input | Column allow-lists | Missing
Data input | Format checks (phone / zip / email / NPI / codes / dates) on server | Missing | Mostly missing
Data input | Length limits on server | Partial | Users only
Files | Upload: safe filename, fixed bucket, owner check | Done
Files | Upload: type / size limits | Missing
Files | Delete: auth / owner | Missing
Files | CSV import: header check | Done | (4 of 5)
Files | CSV import: row validation / size limit | Missing
Output | Angular auto-escaping | Done
Output | bypassSecurityTrustHtml with raw data | Missing | Call list (XSS)
Output | CSV export injection escaping | Missing
Errors | Generic 500s, no SQL leak | Done | Mostly (prismLockedCognitoUser echoes error.message)
Audit | System log written for key actions | Done
Audit | Audit identity set server-side | Missing
CORS | Origin allow-list | Partial | Upload Lambda falls back to http://localhost:4200; others depend on the shared responseHelper layer (not in repo)

## Fix Order
Suggested Fix Order
Source: docs/VALIDATION_AUDIT.md ¦ audit date 2026-10-03 ¦ branch dev ¦ static code review
Step | Scope | Action | Status
1 | P1 #1–#8, #13 | add the existing callerSub -> MEM_USERS -> role/ownership block (already used in prismUpdateUser.js) to every Lambda listed. | Open
2 | P1 #9 | escape fields in calllist-dialog.service.ts (reuse escapeHtml from benefits-dialog.service.ts). | Open
3 | P1 #10–#12 | remove the client secret (public app client), add authGuard + roleGuard on routes, and block the session when the password has expired. | Open
4 | P1 #14 | set added_by / log_by / refer_by from the caller on the server; add per-table column allow-lists. | Open
5 | P2 | align the client password validator, phone/zip/NPI/date validators, file type/size limits, CSV row validation, next-activity date rule. | Open
6 | P3 | duplicate checks, length limits, user-visible error messages, CSV export escaping, remove console.log. | Open