## Summary
PRISM CIH Web - Validation Checklist
Checked against dev branch working tree on 2026-10-06. Status and Priority columns on the detail tabs are editable dropdowns; this summary recalculates from them.
Side | Done | Partial | To Do | Total | % Done | Open P1
Client Side
Server Side
Total
Legend
Done | Implemented
Partial | Partly implemented or inconsistent
To Do | Missing
P1 | Security hole - fix first
P2 | Data integrity / policy gap
P3 | UX / hygiene
Corrections vs. VALIDATION_AUDIT.md (2026-10-03)
- prismUploadplandocument: auth/owner check, directory allow-list, id/env checks are NOT implemented (audit said Done).
- prismGetattachmentListbytypeId: source now in repo; no auth/owner check, no type allow-list.
- prismdeleteAttachment: new replace_url path validates own-bucket URL; still no auth/owner check.

## Client Side
# | Page / Area | Validation / Restriction | Status | Priority | Where / Notes
1 | Login | Username & password required | Done | - | HTML required
2 | Login | OTP exactly 6 digits | Done | - | maxlength=6, pattern, auto-submit
3 | Login | MFA (TOTP setup + verify) | Done | - | Cognito
4 | Login | Failed-attempt counter + lock message | Done | - | 2026-10-06: lock message shown even if the Cognito disable call fails; loginSuccessReset moved after prismAuthentication succeeds (it was clearing LOCKED first); 423 handled. Deploy: lock route must accept calls without a token
5 | Login | Username email format + trim | Done | - | 2026-10-06: trimmed + same EMAIL_RE as server; type=email, maxlength 150
6 | Login | Block login when password expired | Done | - | 2026-10-06: full user (pageAccess) stored only in completeLogin(); expired user gets minimal record for /change-password only
7 | Change Password | New = Confirm | Done | -
8 | Change Password | >=15 chars, upper, lower, digit, special | Done | - | validatePasswordPolicy
9 | Change Password | HTML minlength matches policy | Done | - | 2026-10-07: minlength=15
10 | Change Password | Special-char set matches server | Done | - | 2026-10-07: client now accepts any non-alphanumeric, same as server PASSWORD_POLICY_RE
11 | Change Password | Current password required | Done | - | 2026-10-07: Current Password field, verified via prismAuthentication before changing
12 | Change Password | New != old / password history | Done | - | 2026-10-07: last 5 passwords blocked. prismUserPasswordUpdate checks MEM_USER_PASSWORD_HISTORY (check_only call before Cognito change). Deploy: run lambda-functions/sql/MEM_USER_PASSWORD_HISTORY.sql + deploy lambda
13 | Change Password | Password must not contain name/email | Done | - | 2026-10-07: rejects first name, last name or email local part (3+ chars, case-insensitive)
14 | Add/Edit User | First/Last name required + trim | Done | -
15 | Add/Edit User | Role, Department, Status required | Done | -
16 | Add/Edit User | Duplicate email check | Done | - | checkuserexist; server 409
17 | Add/Edit User | Email format same as server | Done | - | 2026-10-07: Validators.pattern with server EMAIL_RE; trimmed on submit
18 | Add/Edit User | Password policy (15 + complexity) | Done | - | 2026-10-07: shared PasswordPolicyValidator (same regex as server) on add and edit
19 | Add/Edit User | Confirm password field | Done | - | 2026-10-07: CONFIRM PASSWORD field; must match (required when a password is typed)
20 | Add/Edit User | Name max 100 / email max 150 | Done | - | 2026-10-07: Validators.maxLength(100) names, (150) email + input maxlength
21 | Add/Edit User | Name pattern (letters, space, - ') | Done | - | 2026-10-07: letters (any language), space, hyphen, apostrophe; must start with a letter
22 | Add/Edit User | Block whitespace-only names | Done | - | 2026-10-07: nameValidator rejects whitespace-only; values trimmed on submit
23 | Add/Edit User | Admin cannot deactivate self / remove own Admin | Done | - | 2026-10-07: editing own account disables Role and Status; submit also blocks own role/status change and removing own Admin role
24 | New User Request | Required fields | Done | -
25 | New User Request | Phone auto-format, maxlength 14 | Done | -
26 | New User Request | Phone exactly 10 digits | Done | - | 2026-10-07: PhoneDigitsValidator - exactly 10 digits
27 | New User Request | Duplicate email (user / pending request) | Done | - | 2026-10-07: on submit checks prismGetUserByEmail (existing user) and prismUserRequestList (NEW / IN-PROCESS request)
28 | New User Request | Request date not in future | Done | - | 2026-10-07: NotFutureDateValidator + datepicker [max]=today
29 | New User Request | Status not selectable on create | Done | - | 2026-10-07: STATUS hidden on create; always saved as 0 (NEW)
30 | New User Request | Name length / pattern / trim | Done | - | 2026-10-07: shared NameValidator (letters, space, - ', whitespace-only blocked), max 100, trimmed on submit
31 | New User Request | Show error to user | Done | - | 2026-10-07: error line in dialog for save / role-load failures; duplicate email shown under EMAIL
32 | Alternate Address | Address, city, state, zip required | Done | -
33 | Alternate Address | Zip auto-format, maxlength 10 | Done | -
34 | Alternate Address | Zip exactly 5 or 9 digits | Done | - | 2026-10-07: ZipValidator - 12345 or 12345-6789
35 | Alternate Address | State = valid 2-letter code (dropdown) | Done | - | 2026-10-07: STATE is a dropdown of USPS codes (50 states, DC, territories)
36 | Alternate Address | Length limits / trim / whitespace-only | Done | - | 2026-10-07: address max 150, city max 50 (DB column sizes not confirmed); whitespace-only rejected; trimmed on save
37 | Alternate Address | Duplicate address check | Done | - | 2026-10-07: blocks same street+city+state+ZIP5 as primary address or an existing alternate address
38 | Alternate Address | Show error to user | Done | - | 2026-10-07: error line in dialog on save failure / duplicate
39 | Alternate Phone | Required, auto-format, maxlength 14 | Done | -
40 | Alternate Phone | Exactly 10 digits | Done | - | 2026-10-07: PhoneDigitsValidator - exactly 10 digits
41 | Alternate Phone | Not duplicate of primary/other alt phone | Done | - | 2026-10-07: compared by digits against phone, HOME_PHONE, OTHER_PHONE and existing alternate phones
42 | Alternate Phone | Show error to user | Done | - | 2026-10-07: error line in dialog on save failure / duplicate
43 | Plan dialog | Name, start, end, status required | Done | -
44 | Plan dialog | Start <= End | Done | - | Via alert(), not a form validator
45 | Plan dialog | Duplicate plan name | Done | - | 2026-10-07: on submit, case-insensitive match against existing plan names (excluding the plan being edited)
46 | Plan dialog | Name length / trim | Done | - | 2026-10-07: max 100, whitespace-only rejected, trimmed on save
47 | Assign Plan | Plan required | Done | -
48 | Assign Plan | Already-assigned check | Done | - | checkplanexist; doesn't name the member
49 | Assign Plan | Only active / in-date plans selectable | Done | - | 2026-10-07: dropdown lists only status 0 plans with start <= today <= end
50 | File Attachment | File required (new), status required | Done | - | fileattach-dialog.ts
51 | File Attachment | File type allow-list (accept + extension check) | Done | - | 2026-10-07: accept + extension check: pdf, doc(x), xls(x), csv, txt, png, jpg/jpeg
52 | File Attachment | Max file size / empty file | Done | - | 2026-10-07: rejects empty files and files over 10 MB
53 | File Attachment | Delete confirmation | Done | - | 2026-10-07: shared ConfirmDialogComponent replaces native confirm()
54 | Task dialog | Activity, date, assign-to, status required | Done | -
55 | Task dialog | Task date not in past (new task) | Done | - | 2026-10-07: new task: datepicker min = today + validator; edit keeps existing date valid
56 | Task dialog | Note max length | Done | - | 2026-10-07: comment max 500 with counter
57 | Transfer Member | Department, user required | Done | -
58 | Transfer Member | Cannot transfer to current owner | Done | - | 2026-10-07: blocks members already owned by the selected user (uses Care_Coordinator_id added to prismGetUserMemberList - deploy needed for admins)
59 | Transfer Member | Reason required / length | Done | - | 2026-10-07: reason now required, whitespace-only rejected, max 500, trimmed
60 | No-Longer-Patient / Unlock | Note required + trimmed | Done | -
61 | No-Longer-Patient / Unlock | Block whitespace-only note | Done | - | 2026-10-07: NotBlankValidator; Yes now blocked until note valid (was not gated). Unlock dialog now shows the NOTE field (form existed but wasn't rendered); note added to audit log
62 | No-Longer-Patient / Unlock | Note max length | Done | - | 2026-10-07: note max 500 (both dialogs)
63 | Rolewise Page Access | Role, page, status required | Done | -
64 | Rolewise Page Access | Duplicate role + page | Done | - | 2026-10-07: blocks a second row with the same role + page
65 | Rolewise Page Access | Admin cannot remove own access to this page | Done | - | 2026-10-07: editing own role's active PAGE ACCESS row can't change role, page or status
66 | Add Action | Action date valid, digits and / only, maxlength 10 | Done | -
67 | Add Action | Quality gap: TIN, Provider, DOS, flags, SuppSource required | Done | -
68 | Add Action | Quality gap: at least one CPT / HCPCS / ICD-10 | Done | -
69 | Add Action | TIN/Provider conditional required | Done | -
70 | Add Action | Appointment required fields | Done | -
71 | Add Action | PCP visit: date + type required | Done | -
72 | Add Action | Star measure required + duplicate check | Done | -
73 | Add Action | Next activity date required when next activity chosen | To Do | P2 | Server returns 400 otherwise
74 | Add Action | Action date / DOS / PCP date not in future | To Do | P2
75 | Add Action | Next action date >= today | To Do | P3
76 | Add Action | Appointment date not in past | To Do | P3
77 | Add Action | NPI = 10 digits + Luhn | To Do | P2
78 | Add Action | Taxonomy code format (10 chars) | To Do | P3
79 | Add Action | ICD-10 / CPT / HCPCS format | To Do | P2
80 | Add Action | Risk-gap rows required fields | To Do | P2 | Only quality gaps validated
81 | Add Action | Note fields max length | To Do | P3
82 | Process File (CSV) | File required, .csv extension | Done | - | All 5 imports
83 | Process File (CSV) | Exact header match | Done | - | 2026-10-07: Star Performance: requires Measure Name + Statistics + at least one M/D/YYYY date column
84 | Process File (CSV) | Empty file (< 2 rows) | Done | - | 2026-10-07: all 5 imports reject files with no data rows (shared validateCsvRows)
85 | Process File (CSV) | Date normalisation | Done | -
86 | Process File (CSV) | Max file size / row count | Done | - | 2026-10-07: max 25 MB and 100,000 rows (MAX_CSV_MB / MAX_CSV_ROWS in utilities/csv-import.ts)
87 | Process File (CSV) | Row-level checks (required, Medicaid ID, numeric, dates) | Done | - | 2026-10-07: required key columns, dates, numbers per file (ROW_RULES). Required columns inferred - confirm with business
88 | Process File (CSV) | Report bad rows | Done | - | 2026-10-07: upload blocked and bad lines listed (line number + reason) via app-csv-errors
89 | Process File (CSV) | Quoted CSV values | Done | - | 2026-10-07: member file now uses Papa Parse like the others
90 | Process File (CSV) | Duplicate rows within file | Done | - | 2026-10-07: exact duplicate rows reported (star: same measure/statistic/date)
91 | Reports | Start/end required, end >= start | Done | - | Appointments, Action Log, Outreach, Gaps, System Log
92 | Reports | File Log: type + list required | Done | -
93 | Reports | Max date range | Done | - | 2026-10-07: 366-day max (same as server) on Appointments, Action Log, Outreach, Gaps, System Log
94 | Reports | No future dates | Done | - | 2026-10-07: Action Log, Outreach, Gaps, System Log. Appointments allow future (upcoming appointments)
95 | Reports | Member Risk / Star Performance year/plan validation | Done | - | 2026-10-07: Star Performance year/plan required, year list now current year - 4. Member Risk has only a user dropdown - nothing to validate
96 | Reports | CSV export formula escaping (= + - @) | Done | - | 2026-10-07: csvCell() on Appointments, Outreach, Gaps CSV. Pipe-delimited gaps feed unchanged (data format)
97 | Global | Inactivity logout (10 min) | Done | - | auth.service.ts
98 | Global | Token refresh + retry on 401 | Done | - | token.interceptor.ts
99 | Global | Sidebar hides menus by role | Done | - | Cosmetic only
100 | Global | Page access check | Done | - | 2026-10-07: authGuard checks page access before the page loads. Still client-side; Lambdas are the real control
101 | Global | Route guards (auth + role) | Done | - | 2026-10-07: authGuard on every app route (login, pending password change, page access); changePasswordGuard
102 | Global | Escape HTML in call history (XSS) | Done | - | 2026-10-07: shared escapeHtml on call list (and benefits dates); benefits link only for https URLs
103 | Global | Cognito client secret not in browser | Done | - | 2026-10-07: verified - dev uses public app client, no secret/SecretHash in frontend. Prod must also use a public client
104 | Global | Global 403 handler | Done | - | 2026-10-07: interceptor shows a 'no permission' message on 403 when logged in; error still passed to page
105 | Global | Integer-only directives used | Done | - | 2026-10-07: N/A - directives strip leading zeros (breaks OTP). OTP inputs now strip non-digits in onOtpInput
106 | Global | Storage encryption | Done | - | 2026-10-07: decided not to enable - key would ship in bundle. Verified only staff profile stored (tokens in memory); removed unused CryptoService with hard-coded key
107 | Global | Remove console.log (PHI) | Done | - | 2026-10-07: removed outside Add Action (error-reporting, file attach, outreach, importers)
108 | Transfer Member | CLOSE button must not submit the form | Done | - | 2026-10-07: CLOSE had no type, so it submitted the form and could run the transfer; now type="button"
109 | Assign Plan | CLOSE button must not submit the form | Done | - | 2026-10-07: CLOSE had no type, so it could run the assignment; now type="button"
110 | Reports | Appointments SEARCH runs once | Done | - | 2026-10-07: removed duplicate (click) - the form submit already runs applyFilter()
111 | Process File (CSV) | File picker accepts .csv by extension | Done | - | 2026-10-07: all 5 importers check the .csv extension (not MIME), accept=.csv, message shown on rejection
112 | Process File (CSV) | Confirm before PROCESS; warn when error rows exist | Done | - | 2026-10-07: app confirm dialog before PROCESS on all 5 importers; warns with error row count when > 0
113 | Reports | Gaps Report REMOVE uses app confirm dialog | Done | - | 2026-10-07: confirmAction() app dialog replaces native confirm()
114 | Alternate Address | Alternate Address date not in future | Done | - | 2026-10-07: NotFutureDateValidator + datepicker [max]=today. (Stray ~star-performance.html not touched)

## Server Side
# | Lambda / Area | Validation / Restriction | Status | Priority | Where / Notes
1 | prismUploadplandocument | Caller auth (Cognito sub) | To Do | P1 | Only a TODO at line 61 - earlier audit wrongly marked Done
2 | prismUploadplandocument | Role / owner check for plan id | To Do | P1 | Earlier audit wrongly marked Done
3 | prismUploadplandocument | Safe filename (no path traversal) | Done | - | SAFE_FILENAME_RE + no '..'
4 | prismUploadplandocument | Fixed bucket (not from client) | Done | - | ALLOWED_BUCKET
5 | prismUploadplandocument | Signed URL expiry 5 min | Done | -
6 | prismUploadplandocument | CORS origin allow-list + OPTIONS | Partial | P2 | Prod list has http:// dev + localhost; falls back to localhost
7 | prismUploadplandocument | directory allow-list | To Do | P1 | Goes straight into S3 key
8 | prismUploadplandocument | id integer check | To Do | P2
9 | prismUploadplandocument | env allow-list / pattern | To Do | P2
10 | prismUploadplandocument | File type / extension allow-list | To Do | P2
11 | prismUploadplandocument | File size limit | To Do | P2 | Use presigned POST with content-length-range
12 | prismdeleteAttachment | Caller auth + owner check | To Do | P1 | Any id can be deleted or repointed
13 | prismdeleteAttachment | id integer check | Done | -
14 | prismdeleteAttachment | replace_url must be own-bucket https URL | Done | - | isOwnBucketUrl; old URL read from DB
15 | prismGetattachmentListbytypeId | Caller auth + owner check | To Do | P1 | New file, untracked
16 | prismGetattachmentListbytypeId | type_id integer check | Done | -
17 | prismGetattachmentListbytypeId | type allow-list | To Do | P2
18 | prismMultiplefieldupdate | Caller auth + role check | To Do | P1 | Can update ROLE_PAGE_ACCESS, MEM_MEMBERS, etc.
19 | prismMultiplefieldupdate | Table + id-column allow-list, required, no blanks | Done | -
20 | prismMultiplefieldupdate | Column allow-list | To Do | P1
21 | prismMultipleRowAndFieldUpdate | Caller auth + role check | To Do | P1 | Can set Care_Coordinator_id to self
22 | prismMultipleRowAndFieldUpdate | Table + id-column allow-list | Done | -
23 | prismMultipleRowAndFieldUpdate | Column allow-list / max rows / value checks | To Do | P2
24 | prismMultipleRowInsert | Caller auth + Admin gate for ROLE_PAGE_ACCESS | To Do | P1
25 | prismMultipleRowInsert | Table allow-list + required fields | Done | -
26 | prismMultipleinsert | Caller auth | Done | -
27 | prismMultipleinsert | Admin-only for ROLE_PAGE_ACCESS | Partial | P2 | Temp tables not Admin-gated
28 | prismMultipleinsert | Table allow-list, required fields, batching | Done | -
29 | prismMultipleinsert | Column allow-list per table | To Do | P2
30 | prismMultipleinsert | Member ownership for medicaid_id rows | To Do | P2
31 | prismMultipleinsert | Format / length checks (phone, zip, email, dates) | To Do | P2
32 | prismMultipleinsert | Max rows | To Do | P3
33 | All inserts | Audit fields (added_by, log_by, refer_by) set from caller sub | To Do | P1 | Currently trusted from client
34 | prismUpdateCognitoUser | Caller auth + Admin/self check | To Do | P1 | Anyone can reset any password
35 | prismUpdateCognitoUser | Attribute allow-list + password policy | Done | -
36 | prismUpdateCognitoUser | Missing username -> 400 (not 500) | To Do | P3
37 | prismUserPasswordUpdate | Caller auth + ownership | To Do | P1
38 | prismUserPasswordUpdate | ID + password required, 15-char policy | Done | -
39 | prismUserPasswordUpdate | ID integer check | To Do | P3
40 | prismCreateCognitoUser | Caller auth + Admin check | To Do | P1
41 | prismCreateCognitoUser | Email format, policy, numeric role | Done | -
42 | prismCreateUser | Caller auth + Admin check | To Do | P1
43 | prismCreateUser | Required, trim, length, email, status, policy, 409 duplicate | Done | -
44 | prismCreateUser | Role / department exist in master tables | To Do | P2
45 | prismUpdateUser | Caller auth + Admin | Done | -
46 | prismUpdateUser | Required, ints, status, optional policy | Done | -
47 | prismUpdateUser | Name length/trim, role/dept exist, Admin can't demote self | To Do | P2
48 | loginSuccessReset | Caller auth | To Do | P1 | Anyone can clear lockout counter
49 | prismAuthentication | Username/password required, bcrypt, lock check (423), active only | Done | -
50 | prismAuthentication | Non-200 when password expired | To Do | P1
51 | prismAuthentication | Increment failed attempts server-side | To Do | P2
52 | prismAuthentication | Return only caller's role page access | To Do | P3
53 | prismLockedCognitoUser | Caller auth: Admin, or no-token call only when DB LOCKED = 1 | Done | - | 2026-10-06: login page can now disable an account the DB has already locked
54 | prismLockedCognitoUser | No error.message echo | To Do | P3
55 | prismAdminUnLockedCognitoUser | Caller auth + Admin, username required | Done | -
56 | prismdeleteGapObservations | Caller auth, <=500 records, id integer, Type check | Done | -
57 | prismdeleteGapObservations | Record id belongs to subscriber_number | To Do | P2
58 | prismdeleteGapObservations | Admin bypass | To Do | P3 | Admin gets 403
59 | prismUpdategapStatus / prismUpdatequalityStatus | Caller auth + Admin or owner | Done | -
60 | prismUpdategapStatus / prismUpdatequalityStatus | action_id integer + code format | To Do | P3
61 | prismUnSetMemberGapsStatus / prismUnSetqualityStatus | Caller auth + Admin or owner | Done | -
62 | prismUnSetMemberGapsStatus / prismUnSetqualityStatus | action_id type check | To Do | P3 | Bound as VarChar in one
63 | prismUpdatePlanyearForRiskgap | Caller auth + member ownership | To Do | P1
64 | prismUpdatePlanyearForRiskgap | Required, year range | Done | -
65 | prismProcess* (Members/PCR/Quality/Risk) | Caller auth + Admin, session_id numeric | Done | -
66 | prismProcess* (Members/PCR/Quality/Risk) | Validate staged rows before commit | To Do | P2
67 | prismProcessStarPerformanceSeccionID | Source in repo | To Do | P2 | Stub only
68 | prismGetUserMemberList | Caller auth, non-admin forced to self | Done | -
69 | prismGetMemberGapsList / Getcallhistory / MemberAllDetails | Caller auth + Admin or owner | Done | -
70 | prismGetMemberGapsList | Year params checked | To Do | P3
71 | prismGetappointmentList | Caller auth + Admin or owner | Done | -
72 | prismGetappointmentList | Max date range | To Do | P3
73 | prismGetMemberUpcommingTaskList | Caller auth, non-admin forced to self | Done | -
74 | prismLogdetailsbymedicaid | Caller auth + Admin, date checks, max range | Done | -
75 | prismGetPageAccessList / prismUserslist | Caller auth + Admin | Done | -
76 | prismGetproviderIdByTin | TIN = 9 digits | Done | -
77 | prismGetproviderIdByTin | Caller auth | To Do | P3 | Low risk reference data
78 | 27 endpoints with no source in repo | Add source + auth/ownership checks | To Do | P2 | See VALIDATION_AUDIT.md section 2.1; prismGetUserByEmail = email enumeration risk
79 | API Gateway | Cognito authorizer on all routes | Partial | P1 | Confirmed on some; login-flow routes have none
80 | All Lambdas | SQL parameterisation | Done | -
81 | All Lambdas | Generic 500s, no SQL leak | Done | - | Mostly
82 | All Lambdas | System log for key actions | Done | -